## PROJECT
PROJECT TITLE: |  | DEVELOPMENT OF AN ONLINE BUS TICKET BOOKING SYSTEM.
MAIN OBJECTIVE: |  | TO CREATE A SYSTEM WHICH WILL ENABLE MANAGEMENT OF INFORMATION ABOUT PASSENGER, BUS, AGENT, PACKEGE AND SEAT.
SPECIFIC OBJECTIVES: | 1 | Planning about Bus ticket booking online system.
(Depends on the number of your objectives) | 2 | Analysis what problems does the system going solve and identifying the users of the system.
| 3 | Design a sytem of online Bus ticket booking system by using use cases diagrams and flow chart.
| 4 | Implemantation of the system.
| 5 | Maintening the system after being used if there is a presence of any bug.
Identify the stakeholders in your project
| 1 | Project team(Germana, Nicholas, Silvester)
| 2 | Booking Agent
| 3 | Matlab expert
| 4 | bus manager
| 5 | drivers
.
.
.
.
.
.
.
.

## DELIVERABLES
S/N. | GOAL/OBJECTIVE | DELIVERABLE(S) | Estimated Delivery Date
1 | Planning about Bus ticket booking online system. | To create makeup of the project, prepare a document for project team member ,time ,budget,resources,countract, requirements to meet the SMART goal criterion,
2 | Design a sytem of online Bus ticket booking system. | To create wireframe and start coding
3 | Implemantation of the system. | To check if the system will meet the required needs of the client's
4
***You will establish more accurate delivery dates during the scheduling phase, which is next.

## SCHEDULE
S/N. | TASK | LEAD | EFFORT(hours or days or weeks)
1 | Identifying stakeholders(customers,the end user of the product,company,leadersand team members) | Project Manager | 2 days
2 | To make roles and responsibilities (project management skills) | Project Team | 1 day
3 | Prepare a kickoff meeting(To join together workers relationships to build a team) | Project Manager | 10 hrs
4 | Defining project scope,budget and schedule | Project Team | 1 week
5 | Prioritize tasks(Depending on consequences and dependencies) | Project Manager | 2 day
6 | Working on risk assesment | Projecr Team and Manager | whole day
7 | Check and communicate the project plans | Project Team and Manager | 3 days
8 | Gathering requirements from customers | Project Team and Manager | 2 week
.
.
.
.
.

## GANTTCHART
[Project Name] Project Schedule
[Company Name]
| Project Start Date | 2020-07-01 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | [7 empty] | 2020-06-29 | [6 empty] | 2020-07-06 | [6 empty] | 2020-07-13 | [6 empty] | 2020-07-20 | [6 empty] | 2020-07-27 | [6 empty] | 2020-08-03 | [6 empty] | 2020-08-10 | [6 empty] | 2020-08-17
 | time axis 2020-06-29 to 2020-08-23
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2020-06-29 to 2020-08-23
1 | Planning about Bus ticket booking online system. |  |  |  | - |  |  | -
1.1 | Identifying stakeholders | [Name] |  | 2020-07-01 | 2020-07-02 | 2 | 100% | 2
1.2 | To make roles and responsibilities |  |  | 2030-07-02 | 2030-07-02 | 1 | 100% | 1
1.3 | Prepare a kickoff meeting |  |  | 2020-07-03 | 2020-07-03 | 1 | 100% | 1
1.4 | Defining project scope,budget and schedule |  |  | 2020-07-04 | 2020-07-10 | 7 | 100% | 3
1.4.1 | Chake and communicate the project plans |  |  | 2020-07-08 | 2020-07-10 | 3 | 80% | 2
1.4.2 | Gathering requirements from customers |  |  | 2020-07-10 | 2020-07-23 | 14 | 100% | 10
1.5 | [Task] |  |  | 2020-07-12 | 2020-07-14 | 3 | 0% | 3
1.6 | [Task] |  |  | 2020-07-13 | 2020-07-26 | 14 | 0% | 14
1.7 | [Task] |  |  | 2018-02-10 | 2018-02-16 | 7 | 0% | 5
2 | Analysis |  |  |  | - |  |  | -
2.1 | Working on risk assesment |  |  | 2018-02-10 | 2018-02-10 | 1 | 100% | 1
2.2 | Prioritize tasks |  |  | 2018-02-14 | 2018-02-15 | 2 | 100% | 2
2.3 | [Task] |  |  | 2018-02-14 | 2018-02-16 | 3 | 0% | 3
2.4 | [Task] |  |  | 2018-02-17 | 2018-02-22 | 6 | 0% | 4
2.5 | [Task] |  |  | 2018-02-23 | 2018-02-25 | 3 | 0% | 1
3 | Design a sytem of online Bus ticket booking system. |  |  |  | - |  |  | -
3.1 | [Task] |  |  | 2018-02-10 | 2018-02-13 | 4 | 0% | 2
3.2 | [Task] |  |  | 2018-02-14 | 2018-02-16 | 3 | 0% | 3
3.3 | [Task] |  |  | 2018-02-14 | 2018-02-16 | 3 | 0% | 3
3.4 | [Task] |  |  | 2018-02-17 | 2018-02-22 | 6 | 0% | 4
3.5 | [Task] |  |  | 2018-02-23 | 2018-02-25 | 3 | 0% | 1
4 | Implemantation of the system. |  |  |  | - |  |  | -
4.1 | [Task] |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
4.2 | [Task] |  |  | 2018-01-30 | 2018-01-30 | 1 | 0% | 1
4.3 | [Task] |  |  | 2018-01-31 | 2018-01-31 | 1 | 0% | 1
4.4 | [Task] |  |  | 2018-02-01 | 2018-02-01 | 1 | 0% | 1
4.5 | [Task] |  |  | 2018-02-02 | 2018-02-02 | 1 | 0% | 1
-
-
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] |  |  |  | - |  |  | -
1.1 | . [ Level 2 Task ] |  |  |  | - |  |  | -
1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  |  | -
1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  |  | -
► Watch How to Create a Gantt Chart in Excel
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## CONSTRAINTS
S/N. | PROJECT CONSTRAINTS
1 | Time expected to deliver project.
2 | Scope (the expect outcomes of the project).
3 | Budget the amount money that the project has to be given.
4 | Risks that may arise during project management.
5 | Benefits of the project.
6 | Quality required.
.
.
***Project constraints are anything that restricts or dictates the actions of the project team.
https://pmtips.net/article/defining-project-constraints#:~:text=Project%20constraints%20are%20anything%20that,not%20all%20three%20project%20constraints.

## RISK MANAGEMENT
S/N. | RISK | WHAT WILL YOU DO IF HAPPENS |  | WHAT WILL YOU DO TO MITIGATE IT (PREVENT IT FROM HAPPENING)
1 | Understanding of stakeholders (customer) needs or requirement | 1 | education to stakholders(customers) about the system. | 1 | To ensure clear understanding of the system goals.
|  | 2 | To show how the system will be helpful to them | 2 | To ensure awareness among stakeholders
|  | 3 | Preparing of document toshow all essential services that will be provided by the system | 3
4
2 | communication network problems
|  | 1 | To have another alternative source of informations among stakeholders forexample use of magazine,radio also special system when network will not be available | 1 | Keep on advicing stakeholders in use of other alternative source of information.
3 | Unexpected budget cuts
|  | 1 | To reduce some resources which are not nessesary | 1 | To use affordable resource
|  | 2 | To reduce number of requirements | 2 | To stop changing the requirements
4 | Customer review and feedback cycle are too slow
|  | 1 | create a certain notification and attention through the system and weekly reports to ensure active review
5 | Disjoint roles and responsibilities among team members
|  | 1 | assigning task to project team and limit time for accomplish that task so as to ensure active participation | 1 | To educate stakeholders about importance of feedback and review
|  | 2 | To provide motivation more about team work
6 |  | 1
7